## Tasks
Meeting 2025-02-18 --> CHECK START: LINE 31 (Task ID 53) (other tasks above are done and tested)
Main page shared docx |  |  | David's comments David's questions Already read in previous meetings |  | Old codimd notes
Task ID | Task name | Task type Display, Behavior, Code, Documentation or Feature | Comment Anything that can help to understand the task | Status Ready to be tested, Done, To do, Aborted or Pending | Author Helps to remember the discussion | Priority High or Low | Screenshot, file names or link... (optional)
46 | km / s in velocity maps axis | Display | We were talking about the vertical histogram on the right side, I guess | Done | Everybody | High | Units at other places: new issue 49
44 | White bars in fit maps | Feature | Add white bars in the fit maps, link to other bars cleverly | Done | Éric | High
43 | Select window in fit maps automatically | Behavior | When changing the horizontal red bar, update automatically the good window in the list so the users generate the fit maps for the right | Done | Frédéric | High
42 | x rescaling | Feature | Suggest to zoom x only "x rescaling" slider, adjust global behavior as expected | Done | Susanna | High
41 | Do not show message | Behavior | A message still opens whereas it is not useful, to reproduce: Generate fit maps, then before it's done click on a "Fit ..." checkbox in the left menu, the message "In order to see fit maps, ..." is not needed | Done | Éric | Low
40 | Useless message in fit maps | Behavior | A popup still opens whereas the user doesn't need it: - Keep the checkboxes "Fit ..." unchecked - Click on "Generate" to generate fit maps (use a small ROI before to save time) - Wait until the process finishes - Check on a "Fit ..." checkbox --> useless explanation appear | Done | Éric | High
39 | Opening file issue | Code | Trying to open a raster file, but the file keeps uploading indefinitly because of a code error: File "/home/avoyeux/Documents/data_quicklook/processing/data_handling.py", line 320, in set_data_info self.y_fit_bounds[win_key] = [not_nan_indexes[0][0], not_nan_indexes[-1][0]] | Done | Alfred | High | solo_L2_spice-n-ras_20220407T112032_V05_100664102-000.fits
38 | debug.log issue | Code | Avoid git conflits with debug.log logs/debug.log and debug.log are ignored, if there is still a conlit you have to delete the log file the first time if it's a different path. Logs are currently filled in logs/debug.log which is ignored. | Done | Éric | High
37 | Write a developer doc | Documentation | In order to quickly spot the useful available variables and processes, do a list and specify pointers e.g.: - main.windows[i].is_warned tells if user was warned about... - fits_maps_generated[w.win_key] tells if fit maps are generated for this window... | Done | David | Low
36 | Fit maps message once | Behavior | Explain where to find fit maps when they are ready, OK but do it once, see task ID 27 for the complete behavior. | Done | Everybody | High | After the fit is done, when one check the boxes to display the fits, another message tells us to do fits in order to see them. This is not really useful in this case.
35 | Missing file in recent files | Behavior | Do not do anything, just display an error message, do not touch the list (If archives are not mounted yet, we want to keep the data paths) | Done | Everybody | Low
34 | Improve fit bounds and hints | Behavior | Old strategy --> New strategy - No hint for K --> K = 15% of "averaged_not_leved" cube - No hint for σ --> σ = get_σ_nm¹(6) - No hint for I_max --> I_max = max intensity in profile - No hint for λ_mean --> λ_mean = λ matching I_max - Bounds K: [10,40]% of averaged_not_leved cube --> [0,30]% - Bounds σ: [get_σ_nm¹(3), get_σ_nm¹(24)] - Bounds I_max: [80,120]% of max intensity in profile --> unchanged - Bounds λ_max: [80,120]% of λ matching I_max --> unchanged From Eric: px_to_nm(λ(px)) = λ(nm) = (λ(px)−CRPIX3+1)×CDELT3+CRVAL3 From Susanna: FWHM = 6 px (even though doc says 3.8) ¹ => get_σ_nm(FWHM_px) = px_to_nm(FWHM(px) / 2.355) | Done | Everybody | High
33 | Link zoom issue | Behavior | Read checkbox value at loading and apply property as all the others | Done | Alfred | High
31 | Take into account WAVEUNIT | Code | DPDD 4.4.1.3.3: WAVEMIN is the wavelength of the leftmost edge of the first detector pixel column of the readout window, ignoring any binning, and WINWIDTH is the edge-to-edge window width. WAVEMAX is the wavelength corresponding to the rightmost edge of the window’s last pixel column. | Done | Éric | High
30b | Velocity map results | Feature | Replace middle fit map by velocity, used: λ0 = median[map λ_max(x,y)] v = c × (λ_mes−λ0) / λ0 Values are displayed on mouse hover (m/s). Check velocities with one of Slimane’s fits: I do have Slimane's files (level 2.5) to compare Éric: look OK. | Done | Everybody | High
28 | Arrow when hovering bars | Display | Mouse changes to arrow whereas bar isn’t movable | Done | Susanna | High | Looks OK to me (Éric), to be re-tested by Susanna?
27 | Avoid black plots Show "not generated yet" instead | Display | Show "Plot not generated yet" instead of black plots. Behavior: - If fit maps are not generated but at least one "Fit..." checkbox is checked then display text instead of black map - Once fit map is generated: > If all "Fit..." checkbox are unchecked: show explanation pop up > If at least one checkbox is checked: hide text and replace it by the map result > If a Fit checkbox is checked after the fit maps were generated -> Neither the pop up nor text are displayed and do show fit map results OK but better integrate the text "not generated yet" in the frame | Done | Susanna | High
26 | Global levels: values > 100 | Behavior | Values > 100 are not caught properly before being passed to nanpercentile(), fix: thread is abort if min,max are float in [0;100]. Maybe force correct value after computations are finished How did you do? Look at the terminal, I print "Task 26" then min, max right before the nanpercentile call, I can't reproduce values outside [0,100]. You should bypass the condition but I don't remember how | Done | Éric | High
23 | Pane not working for single exposure | Behavior | Let me know Alfred but I think the behavior is correct? Even though you "Link zoom between windows", only pane y is linked because lambda ranges are not the same for each window. | Done | Alfred | High
22 | Hide fit if less than 4 bins to fit | Behavior | Limit fit when at least 4 lambda bins are available, otherwise do not show fit To test it: do "1D averages" over lambda on the first map (x,y) then look at the profile I(lambda) | Done | Everybody | High
20 | Windows briefly open | Display | At least on windows, a window briefly opens at each generation of a plot Culprit: i buttons were "pre-showed", fixed it. | Done | Frédéric | Low
18 | Remove % for "Recovering data file" in the footer | Display | Currently show 1%, add an exception in the footer processes in order to hide % progress | Done | Éric | Low
16 | Link zoom between windows issue | Behavior | The x-lambda axis movements are not the same for both graph Not sure how to reproduce, could you show me again? (after further discussion, seems like it is supposed to be so) | Done | Alfred | High | solo_L2_spice-n-exp_20220407T143611_V04_100664104-000.fits
11 | Accuracy of vertical bar in I(x,y) | Behavior | Moving the x-bar in the x-y plot, does not update always the pixel spectrum. e.g. 3 steps raster. The profile is not updated in the second X-position and the vertical line steps of 4 positions. | Done | Susanna | High | solo_L2_spice-n-ras_20230415T045752_V02_184549775-116.fits
9 | Choose app. name | Documentation | - Minestrone: MINimal Explorer of SPICE … - Instant SPICE - SPICE Peek / Peep / Glance / View / Look / Eye… - SIT / SPICE IT: SPICE Imaging Tool - SPICE IT UP: SPICE Imaging Tool Universal Programme > SPICE up your world / SPICE invaders (SPICE Girls) - SeeIT: SpicE Electronic/Explorer Imaging Tool - QuickSV (Quicklook SPICE Viewer) - QuickSE (Quicklook SPICE Explorer) | Done | Everybody | Low
8 | Fix log and sqrt levels | Behavior | Use log(ax + 1) / log(a + 1) with a = 1000 | Done | Frédéric | High
49 | Units for all maps even when not displaying pixel value | Display | When hovering on a pixel in a Doppler shift (fitted) map, the unit (km/s) is displayed in the (framed) plot title, with the value of the pixel. - This should be generalized to all maps: unit of I and Imax can be taken from the FITS header, v and σ are km/s I am reading the BUNIT keyword in the header, can you confirm it is correct? - The unit should remain displayed even when not hovering on a pixel (when the value is not displayed) Done | Done | Éric | High | Yes, BUNIT for the unit of values in the data cubes
53 | Zoom issues | Behavior | Zooms and panes issues: loop when zoom in deeply, zooming and paning resets the view and other issues (appear when y of (x,y) and (lambda,y) are linked) Also: you can try to hold the right click while moving the mouse to zoom in a map | Ready to be tested | Everybody | High
52 | Remember folder | Feature | Remember folder where last FITS file were picked up | Ready to be tested | Frédéric | Low
52 | Lambda rescaling issue | Feature | When rescaling lambda, the lambda indexes (and related maps) change and shouldn't (blue slider and vertical bars) | Ready to be tested | Everybody | High
21 | Write user documentation | Feature | User documentation in docs/user_manual | Ready to be tested | Everybody | High | User documentation in docs/user_manual
51 | JSON state | Feature | Allow to save and restore the app state thanks to a JSON backup To test it: - Load data (fits file) - Change options (levels, colors, averages, ...) - Save state (State > save state or Alt+S) - Do anything else (load another fits file, change options or even close the app) - Then try State > load state (look for the json saved) (shortcut Alt+L) Works, but plot size saved to 0 ! Smooth 2D not saved either Il serait pratique que le dernier chemin utilisé soit conservé | Ready to be tested | David | High
56 | Fix cancel "Save and load state" | Behavior | Wasn't handled (app froze) | Ready to be tested | Everybody | High
57 | Fix JSON state shortcuts | Behavior | Alt is not a good key, it selects the menu bar on some systems, replaced by Ctrl+Shift+S (and L) | Ready to be tested | Everybody | High
54 | Issue on vertical bars bounds | Behavior | After loading several FITS files, the bounds of the vertical bars are wrong (and default bar position is not centered by default) | Ready to be tested | Everybody | High | Also axis range issue on λ rescaling; probably the same axis value unit conversion issue.
50 | Issue on x rescaling | Behavior | The x axis in fit maps are wrong when "x rescaling" is changed before generating fit maps. The x scale doesn't take into account the scale (study step) and white bars are lost or in wrong position. | Ready to be tested | Éric | High | Also axis range issue on λ rescaling; probably the same axis value unit conversion issue.
45 | Synchronize fit maps zoom | Behavior | Synchronize fit maps zoom | Ready to be tested | Frédéric | High
32 | Show λ unit instead of cube index in maps | Feature | Axes (and sliders) of second map I(lambda y) are adapted to show Angström values, everywhere else lambda indexes and Angström values are displayed | Ready to be tested | Everybody | High
30a | Show unit in velocity map | Feature | Éric: velocity in km/s is now shown in each pixel; it should now also be in km/s instead of m/s in the color bar (previous text is task 46). + The line width map should also be in velocity units of km/s. Is it correct? σ(km/s) = c × (σ(nm) − λ0) / λ0 --> Changer en c × σ(nm) / λ0, ordre de grandeur 1000 km/s with σ(nm) = (λmax - λmin) / len(λ indexes) and λ0 is the median of the fit map λmean (replaced by the velocity map in the display) | Ready to be tested | Éric | High | For width, do not remove λ0. Expected values a few 100s of km/s, positive.
30c | Display of fit results | Behavior | Fit results are clipped by the min max display values. Must be able to adjust the min max like for the other displays. Éric: Fit intensity map could have the same scaling (Linear, Square root...) as the I(x,y) and I(λ, y) maps by default. Apply levels to I_max (first fit map only) | Ready to be tested | Frédéric | High
55 | Remember folder 2 | Behavior | Remember folder when loading a JSON state | Ready to be tested | Everybody | High
14 | Zoom / pane issue | Behavior | Zoom in (x,y) then pane in (λ,y) resets the view | Ready to be tested | Frédéric | High
29 | Default y (red) bars in (x,y) | Behavior | First solution to implement (still including dumbbells): y interval is (min, max) of all pixels on y axis for which any(~isnan(I(:,y,:,:))) Not good enough? see screenshot example col. H where y ∈ [62, 1023] Ask Terje about best way to determine the position of the extrema of the slit in L2 files (= positions of the red bars by default): see Terje's answer --> column J Do we try to replicate the Terje's method in the quicklook app? LET ME KNOW PLEASE :-) | To discuss | Éric | High | #VALUE! | ;; 1: For each detector, make a 1D array containg the intensity ;; along the y direction [::get_y_intensity_both_detectors] ;; 2: Smooth the y intensity arrays heavily in order to estimate the ;; midpoint of the dumbbell (i.e. the upper dumbbell for the SW y ;; intensity array, the lower dummbell for the LW y array). Special ;; care is taken if the dumbbells are not present in the data ;; cube due to a non-standard window height, or if one (or both) of the ;; dumbbells can't be identified (typically if a dumbbell falls ;; off-limb). [::get_dumbbell_max_ix] ;; 3: Take the approximate number of pixels between the dumbbell ;; midpoints and slit edges into account when estimating the slit ;; y range [::get_slit_edge] ;; 5: Set all pixels in the data cube that are below or above the slit y ;; range to NaN
25 | Suggest to edit the offset hint range in fit | Feature | Not much more work if we suggest changing other parameters? Could be a large pop up with inputs? For hints and bounds. Applies to fit maps? | To discuss | Everybody | High
24 | Header values converted | Display | For all i buttons, values have been converted (nm to m, " to degrees, ...) Do not convert and show units | To do | Everybody | High
19 | Smooth 3D | Feature | Replace average 1D / smooth 2D by smooth 3D It could waste important parts of development | Pending | Everybody | Low
17 | Sort processes in footer | Behavior | Sort by running ones, then date | To do | Éric | Low
15 | Center view on λ rescaling | Behavior | Currently centered on the left edge of I(λ,y) I don't know how to tell Pyqtgraph that for the moment | To do | Everybody | High
13 | Zoom axis only | Feature | Idea: mouse wheel when hovering axis: zoom axis only | To do | Frédéric | Low
12 | Vertical scroll larger | Display | Make the vertical scroll bar larger It's the system bar, not Qt | Aborted | Everybody | Low
10 | Update date in recent files | Behavior | Currently it's the first date of loading, we want the last loaded date for each file | To do | Frédéric | Low
7 | Centralize window variables | Code | Then update dev doc | To do | David | Low
48 | Ideas (discussion with Eric last week) | Behavior | We could: - (Done) Save the current app state in a JSON file, then suggest to restore a state - Save the fit maps results somewhere so users could restore one of them (localy priority low) - (No) Even better generate fit maps in crontab so user won't wait anymore - (No) Even better? While generating fit maps, we could highlight interesting results (e.g. velocity maps with structures) | To do | Everybody | High
47 | Create exe | Display |  | To do | Everybody | High