## Program Summary
{{PROJECT_NAME}} — Program Summary
Decision Readiness: ___% | ___ committed pts
PROGRAM TOTALS
Stream | Pts | Tickets | Status | Sprint
Phase 0: Foundation | ___ | {{PREFIX}}-XXX–YYY | Not Started | S1-S3
Feature A: {{Name}} | ___ | {{PREFIX}}-XXX–YYY | Not Started | S4-S6
Feature B: {{Name}} | ___ | {{PREFIX}}-XXX–YYY | Not Started | S5-S8
Feature C: {{Name}} | ___ | {{PREFIX}}-XXX–YYY | Not Started | S7-S9
Phase 2: Hardening | ___ | {{PREFIX}}-XXX–YYY | Not Started | S9-S10
SUMMARY METRICS
Committed points | ___
Backlog/deferred points | ___
Total if everything decomposed | ___
Sprint count | ___
Feature streams | ___
Services/packages | ___
Active tracker issues | ___

## Program Board
Program Board Timeline (S1–S{{N}})
Map feature streams to sprints. Each cell = key deliverable for that sprint.
Stream | Team | Pts | S1 | S2 | S3 | GATE | S4 | S5-S6 | S7-S8 | Notes
Phase 0: Foundation | {{Team}} | ___ | Scaffold | Core | Tests | Review
Feature A | {{Team}} | ___ |  | Design | Impl | Review | Hardening
Feature B | {{Team}} | ___ |  |  |  |  | Scaffold | Core | Integration
Service Migration | {{Team}} | ___ | [5 empty] | Rewrite | Tests

## Sprint 1
Sprint 1 — {{DATES}} — ___ pts
Tip: Group tickets by team. Include only committed work.
{{Team 1}} — ___ pts
ID | Short Desc | Pts | Team | Deps | Notes
{{PREFIX}}-001 | {{Description}} | ___ | {{Team}} | —
{{PREFIX}}-002 | {{Description}} | ___ | {{Team}} | {{PREFIX}}-001
{{PREFIX}}-003 | {{Description}} | ___ | {{Team}} | —

## Sprints 2-N
Sprints 2–{{N}} ({{DATES}})
Add one section per sprint. Copy the table structure from Sprint 1.
Sprint 2 ({{DATES}}) — ___ pts
ID | Short Desc | Pts | Team | Deps | Phase
{{PREFIX}}-XXX | {{Description}} | ___ | {{Team}} | — | {{Phase}}
{{PREFIX}}-XXX | {{Description}} | ___ | {{Team}} | {{DEP}} | {{Phase}}
Sprint 3 ({{DATES}}) — ___ pts
ID | Short Desc | Pts | Team | Deps | Phase
{{PREFIX}}-XXX | {{Description}} | ___ | {{Team}} | — | {{Phase}}

## Phase 1-2 Enablers
Phase 1/2 Enabler Stories
Technical enablers are first-class backlog items with acceptance criteria per SAFe.
{{Service 1}} — ___ stories, ___ pts
ID | Short Desc | Pts | Phase | Sprint | ADRs/Standards
{{PREFIX}}-XXX | TypeScript scaffold | 3 | 1a | S4 | ADR-001, ADR-002
{{PREFIX}}-XXX | Auth middleware | 3 | 1a | S4 | ADR-007
{{PREFIX}}-XXX | Error handling | 2 | 1b | S5 | ADR-006
{{Service 2}} — ___ stories, ___ pts
ID | Short Desc | Pts | Phase | Sprint | ADRs/Standards
{{PREFIX}}-XXX | {{Description}} | ___ | ___ | ___ | ___

## Delivery Teams
Delivery Teams + Agent Mapping
Team | Prefix | S1 Tickets | S1 Pts | Scope
{{Team 1}} | {{PRE}} | {{PREFIX}}-XXX/YYY | ___ | {{Scope}}
{{Team 2}} | {{PRE}} | {{PREFIX}}-XXX/YYY | ___ | {{Scope}}
{{Team 3}} | {{PRE}} | — |  | {{Scope}}
AGENT TEAM MAPPING (if using agentic workflow)
Agent Role | Model Tier | Responsibility | Gate Owner?
BSA | Planning (Opus) | Requirements, specs, AC | No
System Architect | Planning (Opus) | ADR compliance, pattern review | Yes
BE Developer | Execution (Sonnet) | API routes, middleware | No
FE Developer | Execution (Sonnet) | UI components, client logic | No
QAS | Execution (Sonnet) | Testing, AC validation, evidence | Yes
Security Engineer | Execution (Sonnet) | Vuln scanning, auth review | Yes
RTE | Execution (Sonnet) | PR creation, CI monitoring | No
TDM | Execution (Sonnet) | Blocker resolution, updates | No

## Dependencies
Cross-Team Dependencies
Types: Finish-Start, Start-Start, Finish-Finish
ID | From | To | Type | Sprint | Status
D-1 | {{FROM}} | {{TO}} | Finish-Start | S1 wk1 | Active
D-2 | {{FROM}} | {{TO}} | Finish-Start | S1 → S2 | Active
D-3 | {{FROM}} | {{TO}} | Start-Start | S3 | Resolved
D-4 | {{FROM}} | {{TO}} | Finish-Start | S4 → S5 | Active

## ROAM Risks
ROAM Risk Register
R=Resolved, O=Owned, A=Accepted, M=Mitigated
ID | Risk | Impact | Prob | ROAM | Mitigation
R-1 | Agent velocity < projected | High | Med | Owned | S1 is calibration sprint, adjust capacity after
R-2 | Parallel PRs merge conflicts | High | Med | Mitigated | Merge queue + CODEOWNERS + rebase-first
R-3 | Context loss across agent sessions | Med | Med | Mitigated | CLAUDE.md + spec-driven workflow + memory
R-4 | CI/CD pipeline bottleneck | Med | Low | Owned | Path-based triggers, parallel test jobs
R-5 | Scope creep from new requirements | High | Med | Owned | Gate new items through POPM Decision Brief
R-6 | {{Custom risk}} | ___ | ___ | ___ | {{Mitigation}}

## Gate Criteria
Phase Gate Criteria — {{GATE_DATE}}
Types: Must (blocking), Should (tracked), Stretch (aspirational)
# | Criterion | Threshold | Type | Owner
G-01 | Shared packages resolve | npm ls succeeds | Must | {{Team}}
G-02 | Core modules pass tests | 100% pass | Must | {{Team}}
G-03 | CI pipeline green on all services | All checks pass | Must | {{Team}}
G-04 | Security scan clean | No high/critical | Must | {{Team}}
G-05 | Dependency audit clean | npm audit --audit-level=high | Must | {{Team}}
G-06 | API health endpoints | /health/live returns 200 | Must | {{Team}}
G-07 | Test coverage threshold | >=60% line coverage | Should | {{Team}}
G-08 | Documentation complete | ADRs + runbooks merged | Should | {{Team}}
G-09 | {{Custom criterion}} | {{Threshold}} | ___ | {{Owner}}

## POPM Decisions
POPM Pending Decisions
No pending decisions should remain unresolved past PI Planning.
RESOLVED
# | Decision | Status | Date | Impact
1 | {{Decision description}} | DECIDED | {{DATE}} | {{Impact}}
2 | {{Decision description}} | DECIDED | {{DATE}} | {{Impact}}
PENDING
# | Decision | Status | Owner | Deadline
3 | {{Decision description}} | PENDING | {{Owner}} | {{Deadline}}
4 | {{Decision description}} | PENDING | {{Owner}} | {{Deadline}}