## Plan
IronCalc v1.0 · PROJECT PLAN
Read-only sheet. Edit data in 'Tasks' and 'Settings' | [7 empty] | 2026-07-23 | [8 empty] | 2026-08-01 | [30 empty] | 2026-09-01 | [29 empty] | 2026-10-01 | [30 empty] | 2026-11-01
# | Phase | Task | Owner | Start Date | Days | End Date | % Done | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19
1 | Planning | Define scope & goals | John | 2026-07-23 | 4 | 2026-07-27 | 50%
2 | Planning | Stakeholder interviews | John | 2026-07-27 | 3 | 2026-07-30 | 20%
3 | Planning | Requirements doc | John | 2026-07-30 | 5 | 2026-08-04 | 80%
4 | Planning | Tech stack decision | Jane | 2026-08-04 | 3 | 2026-08-07 | 60%
5 | Design | UX wireframes | Jane | 2026-08-07 | 6 | 2026-08-13 | 10%
6 | Design | Design system / tokens | Jane | 2026-08-13 | 5 | 2026-08-18 | 20%
7 | Design | Prototype review | John | 2026-08-18 | 3 | 2026-08-21 | 0%
8 | Dev | Spreadsheet engine core | Jane | 2026-08-21 | 8 | 2026-08-29 | 0%
9 | Dev | Formula parser v2 | Jane | 2026-08-29 | 2 | 2026-08-31 | 0%
10 | Dev | Frontend components | John | 2026-08-31 | 3 | 2026-09-03 | 0%
11 | Dev | WebAssembly build | John | 2026-09-03 | 8 | 2026-09-11 | 0%
12 | Dev | API integration | Jane | 2026-09-11 | 10 | 2026-09-21 | 0%
13 | Testing | Unit test suite | John | 2026-09-21 | 6 | 2026-09-27 | 0%
14 | Testing | Cross-browser QA | Jane | 2026-09-27 | 5 | 2026-10-02 | 0%
15 | Testing | Performance benchmarks | Jane | 2026-10-02 | 5 | 2026-10-07 | 0%
16 | Testing | Bug fixes | John | 2026-10-07 | 5 | 2026-10-12 | 0%
17 | Launch | Docs & changelog | John | 2026-10-12 | 4 | 2026-10-16 | 0%
18 | Launch | Beta release | Jane | 2026-10-16 | 3 | 2026-10-19 | 0%
19 | Launch | Marketing page | Jane | 2026-10-19 | 5 | 2026-10-24 | 0%
20 | Launch | v1.0 release 🚀 | John | 2026-10-24 | 2 | 2026-10-26 | 0%

## Tasks
TASK INPUT
Edit here (plan updates automatically)
# | Phase | Task Name | Owner | Start Date | Days | End Date | % Done | Notes
1 | Planning | Define scope & goals | John | 2026-07-23 | 4 | 2026-07-27 | 50%
2 | Planning | Stakeholder interviews | John | 2026-07-27 | 3 | 2026-07-30 | 20%
3 | Planning | Requirements doc | John | 2026-07-30 | 5 | 2026-08-04 | 80%
4 | Planning | Tech stack decision | Jane | 2026-08-04 | 3 | 2026-08-07 | 60%
5 | Design | UX wireframes | Jane | 2026-08-07 | 6 | 2026-08-13 | 10%
6 | Design | Design system / tokens | Jane | 2026-08-13 | 5 | 2026-08-18 | 20%
7 | Design | Prototype review | John | 2026-08-18 | 3 | 2026-08-21 | 0%
8 | Dev | Spreadsheet engine core | Jane | 2026-08-21 | 8 | 2026-08-29 | 0%
9 | Dev | Formula parser v2 | Jane | 2026-08-29 | 2 | 2026-08-31 | 0%
10 | Dev | Frontend components | John | 2026-08-31 | 3 | 2026-09-03 | 0%
11 | Dev | WebAssembly build | John | 2026-09-03 | 8 | 2026-09-11 | 0%
12 | Dev | API integration | Jane | 2026-09-11 | 10 | 2026-09-21 | 0%
13 | Testing | Unit test suite | John | 2026-09-21 | 6 | 2026-09-27 | 0%
14 | Testing | Cross-browser QA | Jane | 2026-09-27 | 5 | 2026-10-02 | 0%
15 | Testing | Performance benchmarks | Jane | 2026-10-02 | 5 | 2026-10-07 | 0%
16 | Testing | Bug fixes | John | 2026-10-07 | 5 | 2026-10-12 | 0%
17 | Launch | Docs & changelog | John | 2026-10-12 | 4 | 2026-10-16 | 0%
18 | Launch | Beta release | Jane | 2026-10-16 | 3 | 2026-10-19 | 0%
19 | Launch | Marketing page | Jane | 2026-10-19 | 5 | 2026-10-24 | 0%
20 | Launch | v1.0 release 🚀 | John | 2026-10-24 | 2 | 2026-10-26 | 0%
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Formulas:
Start Date = [End Date, row above]
End Date = [Start Date]+[Days]

## Settings
PROJECT SETTINGS
Project Name | IronCalc v1.0 | Name shown on the Plan header
Project Start | 2026-07-23 | First date shown on the Gantt timeline
Days to show | 120 | Number of calendar days in the Gantt (max ~120)
Today | 2026-07-23 | Auto, do not edit
Owner 1 | John
Owner 2 | Jane
Owner 3
Owner 4
Phase colours (reference)
Planning
Design
Dev
Testing
Launch
Other

## METADATA (hidden)
NOW | 46226.5228