## Task Tracker
ID | Phase | Task | Priority | Status | Est. Days | Actual Days | Start Date | Due Date | Completed | Notes
T-001 | Phase 15: Stabilization | Verify and close WI-203 (guard sync CLI) | High | Done | 0.5
T-002 | Phase 15: Stabilization | Verify and close WI-204 (post-merge CI sync) | High | Done | 0.5
T-003 | Phase 15: Stabilization | Add pytest-cov with 80% threshold to CI | Medium | Done | 1 |  |  |  |  | 90.18% achieved
T-004 | Phase 15: Stabilization | Write CONTRIBUTING.md with architecture overview | Medium | Done | 2
T-005 | Phase 15: Stabilization | Fix HTML reporter coverage to 100% | High | Done | 1
T-006 | Phase 16: GitHub Support | Implement DevOpsGitHub provider | High | Done | 4 |  |  |  |  | 24 tests
T-007 | Phase 16: GitHub Support | Implement StandardsGitHub provider | Medium | Done | 3 |  |  |  |  | 9 tests
T-008 | Phase 16: GitHub Support | Add guard sync support for GitHub Issues | High | Done | 2
T-009 | Phase 16: GitHub Support | Add GitHub Actions workflow | Medium | Done | 2 |  |  |  |  | guard-gate.yml
T-010 | Phase 16: GitHub Support | Config validation for GitHub fields | Medium | Done | 1 |  |  |  |  | 9 tests
T-011 | Phase 17: AST Rules | Implement ast_checks.py with 5 AST checks | High | Done | 4 |  |  |  |  | 192 LOC
T-012 | Phase 17: AST Rules | Integrate AST rule type in rules engine | High | Done | 2
T-013 | Phase 17: AST Rules | Create 4 built-in AST rules (BUILTIN-AST-001-004) | High | Done | 2
T-014 | Phase 17: AST Rules | Write AST check and engine tests (50 tests) | High | Done | 2
T-015 | Phase 18: REST API | Implement FastAPI server with 5 endpoints | High | Done | 3 |  |  |  |  | 262 LOC
T-016 | Phase 18: REST API | Add guard serve CLI command | High | Done | 0.5
T-017 | Phase 18: REST API | Add API key authentication | Medium | Done | 1 |  |  |  |  | X-API-Key header
T-018 | Phase 18: REST API | Write 23 API endpoint tests | High | Done | 2
T-019 | Phase 19: Packaging | Finalize pyproject.toml for PyPI-ready build | High | Done | 1 |  |  |  |  | MIT, classifiers, extras
T-020 | Phase 19: Packaging | Write comprehensive README.md | Medium | Done | 2 |  |  |  |  | 159 LOC
T-021 | Phase 19: Packaging | Verify sdist build produces tarball | High | Done | 0.5
T-022 | Phase 20: Deploy & Harden | Write Dockerfile for REST API server | High | Not Started | 1
T-023 | Phase 20: Deploy & Harden | Create docker-compose.yml with config mount | Medium | Not Started | 0.5 |  |  |  |  | Depends on T-022
T-024 | Phase 20: Deploy & Harden | Raise test coverage back above 90% | High | Not Started | 2 |  |  |  |  | Currently 87.51%
T-025 | Phase 20: Deploy & Harden | Add health check and restart policy to Docker | Low | Not Started | 0.5 |  |  |  |  | Depends on T-022
T-026 | Phase 20: Deploy & Harden | Write internal deployment guide | Medium | Not Started | 1
T-027 | Phase 21: Packs & Docs | Create OWASP Top 10 standards pack | High | Not Started | 4
T-028 | Phase 21: Packs & Docs | Create SOC2 or HIPAA standards pack | Medium | Not Started | 4
T-029 | Phase 21: Packs & Docs | Write internal user guide (install, config, rules, packs) | Medium | Not Started | 3
T-030 | Phase 21: Packs & Docs | Write API reference documentation | Medium | Not Started | 2
T-031 | Phase 22: Custom Rules | Design custom rule DSL (YAML-based) | High | Not Started | 2
T-032 | Phase 22: Custom Rules | Implement custom rule loader | High | Not Started | 4 |  |  |  |  | Depends on T-031
T-033 | Phase 22: Custom Rules | Support user-defined AST checks via config | Medium | Not Started | 3 |  |  |  |  | Depends on T-032
T-034 | Phase 22: Custom Rules | Write extension guide with examples | Medium | Not Started | 2
T-035 | Phase 22: Custom Rules | Write tests for custom rule loading | High | Not Started | 2 |  |  |  |  | Depends on T-032
T-036 | Phase 23: Jira & Perf | Implement DevOpsJira provider | High | Not Started | 5
T-037 | Phase 23: Jira & Perf | Implement StandardsJira provider | Medium | Not Started | 3
T-038 | Phase 23: Jira & Perf | Performance benchmarking on 10k+ file repos | Medium | Not Started | 2
T-039 | Phase 23: Jira & Perf | Incremental scanning optimizations | Medium | Not Started | 4
T-040 | Phase 23: Jira & Perf | Write Jira integration tests | High | Not Started | 2 |  |  |  |  | Depends on T-036, T-037
T-041 | Phase 24: IDE & ML | Build VS Code extension (scan-on-save) | High | Not Started | 7
T-042 | Phase 24: IDE & ML | ML-based severity estimation prototype | Medium | Not Started | 5
T-043 | Phase 24: IDE & ML | Write internal pack authoring guide | Medium | Not Started | 2
Summary
|  | Total Tasks | 43
|  | Done | 21
|  | In Progress | 0
|  | Not Started | 22
|  | Blocked | 0
|  | Total Est. Days | 98
|  | % Complete | 48.84%

## Burndown
Week | Date | Tasks Remaining | Tasks Completed (Cumulative) | Notes
1 | 2026-03-01 | 22 | 21 | Phases 15-19 complete. 21 done, 22 remaining.
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20