## Annotated Runs
platform | run_folder_name | s3_uri | transfer_state | oow_done_at | sample_intent | prior_ursa_trigger_euid | prior_ursa_job_euid | prior_ursa_status | bloom_euid | dewey_artifact_euid | dewey_bloom_relation_euid | fresh_ursa_trigger_euid | fresh_ursa_workset_euid | fresh_ursa_manifest_euid | fresh_ursa_analysis_job_euids | fresh_ursa_status | dyec_fallback_expt_id | dyec_fallback_run_id | command_ids | notes | sample_sheet_key | sample_sheet_samples_count | demux_barcodes_with_meaningful_data_count | demux_barcodes_with_meaningful_data | samples_in_run | coriell_ids | coriell_known_for | other_helpful_info | cluster_analysis_running_on | run_qc_analysis_euid | run_qc_s3_prefix | runqc_multiqc_html | variant_calling_analysis_euid | variant_calling_analysis_qc_dirs | ledger_run_id | plan_order | execution_group | assigned_agent | ledger_status | hold_reason | concurrency_slots_required | fastq_or_basecall_state | dra_mount_id | dra_status | mounted_run_dir | run_context_tsv_status | samples_tsv_status | units_tsv_status | runqc_analysis_euid_decision | variant_analysis_euid_decision | ursa_action_required | planned_runqc_command_id | planned_variant_command_id | planned_dayoa_profile | planned_day_clone_destination | planned_day_clone_executing_entity | tmux_session | dyec_workflow_session | runqc_terminal_state | variant_terminal_state | export_status | export_destination | export_receipt_path | fsx_delete_gate_status | fsx_delete_candidate_path | hybrid_candidate_status | ledger_notes
ILMN | 20260526_LH01121_0004_B23WW2NLT4 | s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/lh01121/2026/20260526_LH01121_0004_B23WW2NLT4/ | OOW.done | 2026-05-29T11:46:02+00:00 | Altair/MAWI/NA validation-style ILMN run; NovaSeq X Plus B4; 49 dual-indexed samples; Y151/I10/I10/Y151. | URDT-93BE1C31F5A2BAA6 | M-RGX-9WR2 | FAILED;jobs=FAILED | M-BRM-6V | M-DGX-9SSE | M-DGX-9SX6 |  |  |  |  | HTTP_503 |  |  | illumina_run_qc_bclconvert | Bloom sidecar reused ¦ Dewey sidecar reused ¦ Dewey-Bloom relation existing M-DGX-9SX6 ¦ Ursa policy incomplete; later fresh Ursa requests blocked | s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/lh01121/2026/20260526_LH01121_0004_B23WW2NLT4/SampleSheet.csv | 49 | not assessed - no BCLConvert output in raw run prefix | not found; sample sheet has 49 index pairs | Altair-HG001-a,Altair-HG001-b,Altair-HG001-c,Altair-HG002-a,Altair-HG002-b,Altair-HG002-c,Altair-HG003-a,Altair-HG003-b,Altair-HG003-c,Altair-HG004-a,Altair-HG004-b,Altair-HG004-c,Altair-HG005-a,Altair-HG005-b,Altair-HG005-c,Altair-HG006-a,Altair-HG006-b,Altair-HG006-c,Altair-HG007-a,Altair-HG007-b,Altair-HG007-c,Altair-BUCCAL1-a,Altair-BUCCAL1-b,Altair-BUCCAL2-a,Altair-BUCCAL2-b,Altair-BUCCAL3-a,Altair-BUCCAL3-b,Altair-BUCCAL4-a,Altair-BUCCAL5-a,Altair-BUCCAL6-a,Altair-BUCCAL7-a,Altair-BUCCAL8-a,Altair-BUCCAL9-a,Altair-NA05115-a,Altair-NA09216-a,Altair-NA07439-a,Altair-NA20241-a,Altair-NA05212-a,Altair-NA15849-a,Altair-NA20208-a,Altair-NTC,mawi-hybrid-Spec_19,mawi-hybrid-Spec_22,mawi-hybrid-Spec_23,mawi-hybrid-Spec_24,NA00232-SMN,NA09677-SMN,NA03986-DMPK,NA05164-DMPK | NA00232,NA03986,NA05115,NA05164,NA05212,NA07439,NA09216,NA09677,NA15849,NA20208,NA20241 | Run-file labels identify NA00232 and NA09677 as SMN samples, NA03986 and NA05164 as DMPK samples; other NA IDs are Coriell-style IDs but exact catalogue annotations were not present in run files. | BCLConvert_Data section; OverrideCycles Y151/I10/I10/Y151; includes HG001-HG007 reference-style samples, buccal samples, MAWI hybrid specimens, NTC, SMN-labelled, and DMPK-labelled samples. | dyec-test (prior failed Ursa trigger) | M-RGX-9WR2 | not found from Ursa readback | not found | not found | not found | RUN-001 | 1 | single-run lane; BCLConvert/demux required | Agent 1 ledger; Agent 2 mounts; Agent 3 Ursa/manifests; Agent 4 runQC; Agent 5 variant/export/hybrid | PLANNED_GATE0 |  | 2 | needs_bclconvert_or_demux; no BCLConvert output assessed in raw prefix | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MANIFEST | TO_FILL_AFTER_MANIFEST | TO_FILL_AFTER_MANIFEST | prior failed M-RGX-9WR2; ask Ursa if reusable, otherwise request new runQC EUID | missing/not found; request new variant analysis EUID after runQC/BCL outputs | required: failed prior or incomplete policy | illumina_run_qc_bclconvert | germline_wgs_kitchensink target bundle; catalog gap row if DYEC command missing requested targets | hg38_broad | $RUNQC_OR_VARIANT_ANALYSIS_EUID | BigB-4-mk | TO_FILL_ON_LAUNCH | TO_FILL_ON_LAUNCH | TO_FILL_ON_COMPLETION | TO_FILL_ON_COMPLETION | TO_FILL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | PENDING_EXPLICIT_APPROVAL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | candidate discovery after runQC/sample identity mapping | initial annotation before live plan execution; original spreadsheet preserved; DayOA git tag required 2.0.43
ILMN | 20260526_LH01121_0003_A23WW2YLT4 | s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/lh01121/2026/20260526_LH01121_0003_A23WW2YLT4/ | no_oow_done |  | Control ILMN run; NovaSeq X Plus B4; root SampleSheet.csv not found in earlier inspection; Y151/I8/I8/Y151. |  |  |  | M-BRM-5X | M-DGX-9SKT | M-DGX-9SQJ |  |  |  |  | HELD_NO_OOW_DONE |  |  | illumina_run_qc_bclconvert | Bloom sidecar reused ¦ Dewey sidecar reused ¦ Dewey-Bloom relation existing M-DGX-9SQJ ¦ Fresh Ursa request held because OOW.done is absent | not found at run root | 0 | not assessed - no root sample sheet and no OOW.done | not found | not found |  |  | Control run from RunParameters; root SampleSheet.csv not found; OOW.done absent so Ursa held. | none - no OOW.done | [5 empty] | RUN-HOLD-001 | HOLD | held | Agent 1 ledger; Agent 2 mounts; Agent 3 Ursa/manifests; Agent 4 runQC; Agent 5 variant/export/hybrid | HELD | transfer_state is no_oow_done; root sample sheet/sample count absent; do not mount or run | 0 | blocked_before_mount | [6 empty] | held; no EUID request until OOW.done/sample sheet present | held; no EUID request until runQC eligible | none while held | illumina_run_qc_bclconvert | germline_wgs_kitchensink target bundle; catalog gap row if DYEC command missing requested targets | [13 empty] | initial annotation before live plan execution; original spreadsheet preserved; DayOA git tag required 2.0.43
ONT | 20260522_ONT_4Coriells_chip2 | s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/pca100/2026/20260522_ONT_4Coriells_chip2/ | OOW.done | 2026-05-27T00:43:25+00:00 | PromethION Coriell test/validation run; SQK-NBD114-24; 24 barcode rows labelled test_sample; flow cell PBM14931 position 1C. |  |  |  | M-BRN-22 | M-DGX-9YS9 | M-DGX-9YX1 |  |  |  |  | BLOCKED_URSA_POLICY_INCOMPLETE |  |  | ont_run_qc | Bloom created M-BRN-22 ¦ Bloom json_addl.properties.name/run_name match folder; top-level name remains template display; authenticated rename returned 403 ¦ Dewey registered M-DGX-9YS9 ¦ Dewey-Bloom relation created M-DGX-9YX1 ¦ Fresh Ursa request skipped after earlier policy-incomplete response | s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/pca100/2026/20260522_ONT_4Coriells_chip2/20260522_ONT_4Coriells_chip2/20260523_0038_1C_PBM14931_9bbdbb3f/sample_sheet_PBM14931_20260523_0016_9bbdbb3f.csv | 1 | 22 | barcode01,barcode02,barcode03,barcode05,barcode06,barcode07,barcode08,barcode09,barcode10,barcode11,barcode12,barcode14,barcode15,barcode16,barcode17,barcode18,barcode19,barcode20,barcode21,barcode22,barcode23,barcode24 | sample_sheet sample_id=20260522_ONT_4Coriells_chip2; barcode_alignment has 24 barcode rows labelled test_sample plus unclassified |  | No NA/GM Coriell identifier present in run sample_sheet or barcode_alignment; run files identify Coriell chip test run only. | Flow cell PBM14931, position 1C; SQK-NBD114-24; barcode_alignment target_unclassified is zero for barcode04 and barcode13; barcode_alignment=s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/pca100/2026/20260522_ONT_4Coriells_chip2/20260522_ONT_4Coriells_chip2/20260523_0038_1C_PBM14931_9bbdbb3f/barcode_alignment_PBM14931_9bbdbb3f_7e492b4e.tsv | none - fresh Ursa skipped after policy blocker | [5 empty] | RUN-002 | 2 | two-run lane if FASTQs confirmed present | Agent 1 ledger; Agent 2 mounts; Agent 3 Ursa/manifests; Agent 4 runQC; Agent 5 variant/export/hybrid | PLANNED_GATE0 |  | 1 | fastq presence to verify before launch; ONT basecalling policy/EUID blocker noted | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MANIFEST | TO_FILL_AFTER_MANIFEST | TO_FILL_AFTER_MANIFEST | request runQC EUID or unblock existing Ursa policy before launch | request variant EUID after runQC inputs are materialized | required: BLOCKED_URSA_POLICY_INCOMPLETE | ont_run_qc | ont_snv_alignstats_kitchensink plus contam/multiqc_final; catalog gap row if contam target unavailable | hg38_broad | $RUNQC_OR_VARIANT_ANALYSIS_EUID | BigB-4-mk | TO_FILL_ON_LAUNCH | TO_FILL_ON_LAUNCH | TO_FILL_ON_COMPLETION | TO_FILL_ON_COMPLETION | TO_FILL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | PENDING_EXPLICIT_APPROVAL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | candidate discovery after runQC/sample identity mapping | initial annotation before live plan execution; original spreadsheet preserved; DayOA git tag required 2.0.43
ONT | 20260522_ONT_4Coriells_chip4 | s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/pca100/2026/20260522_ONT_4Coriells_chip4/ | OOW.done | 2026-05-26T21:37:04+00:00 | PromethION Coriell test/validation run; SQK-NBD114-24; 24 barcode rows labelled test_sample; flow cell PBM13048 position 3E. |  |  |  | M-BRN-30 | M-DGX-9YZX | M-DGX-9Z3N |  |  |  |  | BLOCKED_URSA_POLICY_INCOMPLETE |  |  | ont_run_qc | Bloom created M-BRN-30 ¦ Bloom json_addl.properties.name/run_name match folder; top-level name remains template display; authenticated rename returned 403 ¦ Dewey registered M-DGX-9YZX ¦ Dewey-Bloom relation created M-DGX-9Z3N ¦ Fresh Ursa request skipped after earlier policy-incomplete response | s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/pca100/2026/20260522_ONT_4Coriells_chip4/20260522_ONT_4Coriells_chip4/20260523_0039_3E_PBM13048_8867cb21/sample_sheet_PBM13048_20260523_0015_8867cb21.csv | 1 | 21 | barcode01,barcode02,barcode03,barcode04,barcode05,barcode06,barcode07,barcode10,barcode11,barcode12,barcode13,barcode14,barcode15,barcode16,barcode17,barcode18,barcode19,barcode20,barcode21,barcode22,barcode24 | sample_sheet sample_id=20260522_ONT_4Coriells_chip4; barcode_alignment has 24 barcode rows labelled test_sample plus unclassified |  | No NA/GM Coriell identifier present in run sample_sheet or barcode_alignment; run files identify Coriell chip test run only. | Flow cell PBM13048, position 3E; SQK-NBD114-24; barcode_alignment target_unclassified is zero for barcode08, barcode09, and barcode23; barcode_alignment=s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/pca100/2026/20260522_ONT_4Coriells_chip4/20260522_ONT_4Coriells_chip4/20260523_0039_3E_PBM13048_8867cb21/barcode_alignment_PBM13048_8867cb21_f20c3bb7.tsv | none - fresh Ursa skipped after policy blocker | [5 empty] | RUN-003 | 3 | two-run lane if FASTQs confirmed present | Agent 1 ledger; Agent 2 mounts; Agent 3 Ursa/manifests; Agent 4 runQC; Agent 5 variant/export/hybrid | PLANNED_GATE0 |  | 1 | fastq presence to verify before launch; ONT basecalling policy/EUID blocker noted | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MANIFEST | TO_FILL_AFTER_MANIFEST | TO_FILL_AFTER_MANIFEST | request runQC EUID or unblock existing Ursa policy before launch | request variant EUID after runQC inputs are materialized | required: BLOCKED_URSA_POLICY_INCOMPLETE | ont_run_qc | ont_snv_alignstats_kitchensink plus contam/multiqc_final; catalog gap row if contam target unavailable | hg38_broad | $RUNQC_OR_VARIANT_ANALYSIS_EUID | BigB-4-mk | TO_FILL_ON_LAUNCH | TO_FILL_ON_LAUNCH | TO_FILL_ON_COMPLETION | TO_FILL_ON_COMPLETION | TO_FILL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | PENDING_EXPLICIT_APPROVAL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | candidate discovery after runQC/sample identity mapping | initial annotation before live plan execution; original spreadsheet preserved; DayOA git tag required 2.0.43
ONT | 20260522_ONT_4Coriells_chip1 | s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/pca100/2026/20260522_ONT_4Coriells_chip1/ | OOW.done | 2026-05-26T19:34:28+00:00 | PromethION Coriell test/validation run; SQK-NBD114-24; 24 barcode rows labelled test_sample; flow cell PBM13545 position 2B. |  |  |  | M-BRN-4Y | M-DGX-9Z5H | M-DGX-9Z99 |  |  |  |  | BLOCKED_URSA_POLICY_INCOMPLETE |  |  | ont_run_qc | Bloom created M-BRN-4Y ¦ Bloom json_addl.properties.name/run_name match folder; top-level name remains template display; authenticated rename returned 403 ¦ Dewey registered M-DGX-9Z5H ¦ Dewey-Bloom relation created M-DGX-9Z99 ¦ Fresh Ursa request skipped after earlier policy-incomplete response | s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/pca100/2026/20260522_ONT_4Coriells_chip1/20260522_ONT_4Coriells_chip1/20260522_2252_2B_PBM13545_f3392d36/sample_sheet_PBM13545_20260522_2220_f3392d36.csv | 1 | 24 | barcode01,barcode02,barcode03,barcode04,barcode05,barcode06,barcode07,barcode08,barcode09,barcode10,barcode11,barcode12,barcode13,barcode14,barcode15,barcode16,barcode17,barcode18,barcode19,barcode20,barcode21,barcode22,barcode23,barcode24 | sample_sheet sample_id=20260522_ONT_4Coriells_chip1; barcode_alignment has 24 barcode rows labelled test_sample plus unclassified |  | No NA/GM Coriell identifier present in run sample_sheet or barcode_alignment; run files identify Coriell chip test run only. | Flow cell PBM13545, position 2B; SQK-NBD114-24; all 24 barcode_alignment rows have nonzero target_unclassified; barcode_alignment=s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/pca100/2026/20260522_ONT_4Coriells_chip1/20260522_ONT_4Coriells_chip1/20260522_2252_2B_PBM13545_f3392d36/barcode_alignment_PBM13545_f3392d36_eb9b0a06.tsv | none - fresh Ursa skipped after policy blocker | [5 empty] | RUN-004 | 4 | two-run lane if FASTQs confirmed present | Agent 1 ledger; Agent 2 mounts; Agent 3 Ursa/manifests; Agent 4 runQC; Agent 5 variant/export/hybrid | PLANNED_GATE0 |  | 1 | fastq presence to verify before launch; ONT basecalling policy/EUID blocker noted | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MANIFEST | TO_FILL_AFTER_MANIFEST | TO_FILL_AFTER_MANIFEST | request runQC EUID or unblock existing Ursa policy before launch | request variant EUID after runQC inputs are materialized | required: BLOCKED_URSA_POLICY_INCOMPLETE | ont_run_qc | ont_snv_alignstats_kitchensink plus contam/multiqc_final; catalog gap row if contam target unavailable | hg38_broad | $RUNQC_OR_VARIANT_ANALYSIS_EUID | BigB-4-mk | TO_FILL_ON_LAUNCH | TO_FILL_ON_LAUNCH | TO_FILL_ON_COMPLETION | TO_FILL_ON_COMPLETION | TO_FILL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | PENDING_EXPLICIT_APPROVAL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | candidate discovery after runQC/sample identity mapping | initial annotation before live plan execution; original spreadsheet preserved; DayOA git tag required 2.0.43
ILMN | 20260522_LH01106_0010_A23VM5CLT4 | s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/LH01106/2026/20260522_LH01106_0010_A23VM5CLT4/ | OOW.done | 2026-05-25T05:13:49+00:00 | 23andMe run 3 ILMN run; NovaSeq X Plus B4; 94 dual-indexed samples; Y151/I10/I10/Y151. | URDT-6844A94027E8A699 | M-RGX-9T77 | FAILED;jobs=FAILED | M-BRM-8Q | M-DGX-9TV9 | M-DGX-9TZ1 |  |  |  |  | BLOCKED_URSA_POLICY_INCOMPLETE |  |  | illumina_run_qc_bclconvert | Bloom sidecar reused ¦ Dewey sidecar reused ¦ Dewey-Bloom relation existing M-DGX-9TZ1 ¦ Fresh Ursa request skipped after earlier policy-incomplete response | s3://lsmc-ssf-sequencing-data/basecalls/lsmc/ssf-hq/LH01106/2026/20260522_LH01106_0010_A23VM5CLT4/SampleSheet.csv | 94 | not assessed - no BCLConvert output in raw run prefix | not found; sample sheet has 94 index pairs | s74478,s77407,s77409,s77414,s77586,s77669,s77672,s77674,s77676,s77677,s77678,s77679,s77680,s77681,s77683,s77684,s77685,s77687,s77688,s77689,s77690,s77691,s77694,s77695,s77699,s77700,s77701,s77702,s77703,s77704,s77705,s77706,s77707,s77710,s77711,s77712,s77713,s77714,s77715,s77716,s77717,s77718,s77719,s77720,s77721,s77722,s77723,s77724,s77725,s77726,s77728,s77733,s77734,s77735,s77736,s77738,s77744,s77745,s77748,s77750,s77753,s77754,s77756,s77757,s77758,s77759,s77760,s77761,s77762,s77763,s77764,s77765,s77766,s77767,s77768,s77770,s77771,s77773,s77433,s77780,s77775,s77483,s77787,s77794,s77804,s77802,s77778,s77790,s77783,s77784,s77785,s77786,s77791,s77612 |  |  | BCLConvert_Data section; OverrideCycles Y151/I10/I10/Y151; 23andMe run 3 sample set. | xfer-cluster (prior failed Ursa trigger) | M-RGX-9T77 | not found from Ursa readback | not found | not found | not found | RUN-005 | 5 | single-run lane; BCLConvert/demux required | Agent 1 ledger; Agent 2 mounts; Agent 3 Ursa/manifests; Agent 4 runQC; Agent 5 variant/export/hybrid | PLANNED_GATE0 |  | 2 | needs_bclconvert_or_demux; no BCLConvert output assessed in raw prefix | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MOUNT | TO_FILL_AFTER_MANIFEST | TO_FILL_AFTER_MANIFEST | TO_FILL_AFTER_MANIFEST | prior failed M-RGX-9T77; ask Ursa if reusable, otherwise request new runQC EUID | missing/not found; request new variant analysis EUID after runQC/BCL outputs | required: failed prior or incomplete policy | illumina_run_qc_bclconvert | germline_wgs_kitchensink target bundle; catalog gap row if DYEC command missing requested targets | hg38_broad | $RUNQC_OR_VARIANT_ANALYSIS_EUID | BigB-4-mk | TO_FILL_ON_LAUNCH | TO_FILL_ON_LAUNCH | TO_FILL_ON_COMPLETION | TO_FILL_ON_COMPLETION | TO_FILL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | PENDING_EXPLICIT_APPROVAL_AFTER_EXPORT | TO_FILL_AFTER_EXPORT | candidate discovery after runQC/sample identity mapping | initial annotation before live plan execution; original spreadsheet preserved; DayOA git tag required 2.0.43

## Plan Columns
Generated at | 2026-06-03T15:57:41.068375+00:00
Source TSV | /Users/jmajor/Downloads/20260603T151652Z_run_directory_dayhoff_qc_backfill_report.tsv
Annotated TSV | /Users/jmajor/.codex/worktrees/be82/daylily-ephemeral-cluster/docs/plans/20260603T151652Z_run_directory_dayhoff_qc_backfill_annotated_start.tsv
Cluster | BigB-4-mk
Concurrency rule | 2 active run dirs max; BCLConvert/basecalling/demux consumes both slots
Cleanup rule | FSx deletion remains gated until export verification and explicit approval
New column | Intended fill point
ledger_run_id | Gate 0 initial annotation or ledger update
plan_order | Gate 0 initial annotation or ledger update
execution_group | Gate 0 initial annotation or ledger update
assigned_agent | Gate 0 initial annotation or ledger update
ledger_status | Gate 0 initial annotation or ledger update
hold_reason | Gate 0 initial annotation or ledger update
concurrency_slots_required | Gate 0 initial annotation or ledger update
fastq_or_basecall_state | Gate 0 initial annotation or ledger update
dra_mount_id | Agent 2 after DRA mount/create/poll
dra_status | Agent 2 after DRA mount/create/poll
mounted_run_dir | Agent 2 after DRA mount/create/poll
run_context_tsv_status | Agent 3 after manifest generation
samples_tsv_status | Agent 3 after manifest generation
units_tsv_status | Agent 3 after manifest generation
runqc_analysis_euid_decision | Agent 3 after Ursa resolve/request decision
variant_analysis_euid_decision | Agent 3 after Ursa resolve/request decision
ursa_action_required | Agent 3 after Ursa resolve/request decision
planned_runqc_command_id | Gate 0 initial annotation or ledger update
planned_variant_command_id | Gate 0 initial annotation or ledger update
planned_dayoa_profile | Gate 0 initial annotation or ledger update
planned_day_clone_destination | Gate 0 initial annotation or ledger update
planned_day_clone_executing_entity | Gate 0 initial annotation or ledger update
tmux_session | Agent 4/5 at launch
dyec_workflow_session | Agent 4/5 at launch
runqc_terminal_state | Agent 4/5 at completion/blocker
variant_terminal_state | Agent 4/5 at completion/blocker
export_status | Agent 5 after export verification / cleanup gate
export_destination | Agent 5 after export verification / cleanup gate
export_receipt_path | Agent 5 after export verification / cleanup gate
fsx_delete_gate_status | Agent 5 after export verification / cleanup gate
fsx_delete_candidate_path | Agent 5 after export verification / cleanup gate
hybrid_candidate_status | Gate 0 initial annotation or ledger update
ledger_notes | Gate 0 initial annotation or ledger update
DayOA git tag override | 2.0.43 required by user; use --git-tag 2.0.43 and day-clone -t 2.0.43