## Cover
OpenPitch — PM Workbook
KPIs · Launch Gates · Cost Model · Risk Register · Roadmap
Owner: Mohamed Abdulhadi · Updated: 2026-06-14
Tab | Purpose
KPI Tracker | North-star + activation/trust/usage/community metrics with targets and weekly star milestones
Launch Gates | Go/no-go checklist (auto % complete) — must all be Done before public launch
Cost Model | Proves the zero-cost claim: free-tier capacity vs daily demand, and cost-if-paid
Risk Register | Likelihood × impact scoring with mitigations and owners
Roadmap | Time-boxed phases and milestones
Legend
Blue text = input you change
Black text = formula (auto-calculated)

## KPI Tracker
Category | Metric | Definition | Target | Current | Gap
North Star | Weekly returning MCP users | Distinct users who query OpenPitch in-agent ≥1×/wk | 50 | 0 | 50
Activation | Time-to-first-answer (sec) | README → first sourced answer | 60 | 0 | 60
Activation | Clean-machine install success % | Fresh-machine MCP install works | 100% | 0% | 100%
Trust | % metrics with full provenance | value+source+confidence+as_of | 100% | 100% | 0%
Trust | Correction issues resolved | Accepted public corrections | 10 | 0 | 10
Trust | Confirmed:contradicted ratio | Claims later confirmed vs contradicted | 3 | 0 | 3
Usage | MCP tool calls / week | Across demos + real users | 500 | 0 | 500
Usage | Event-feed / recipe consumers | Downstream integrations | 10 | 0 | 10
Usage | Dashboard visits / week | Static dashboard traffic | 1000 | 0 | 1000
Community | GitHub stars (30-day) | Launch-window stars | 5000 | 0 | 5000
Community | Contributors | Distinct PR authors | 15 | 0 | 15
Community | PRs (data/sources/adapters) | Community contributions | 25 | 0 | 25
Weekly star milestones
Week | Target | Actual | On track?
Week 1 | 1000 | 0 | No
Week 2 | 2500 | 0 | No
Week 3 | 4000 | 0 | No
Week 4 | 5000 | 0 | No

## Launch Gates
Launch readiness — all gates must be Done before public launch
% complete: | 0%
# | Gate | Required | Status | Owner | Target date | Notes
1 | Credible seed dataset (10 cos, 3+ sourced metrics) | Yes | Not started
2 | Working MCP read path (tools return + no-data handled) | Yes | Not started
3 | Provenance on every metric (source+confidence+as_of) | Yes | Not started
4 | 2–3 strong public-source contradictions | Yes | Not started
5 | Correction workflow + issue template | Yes | Not started
6 | Methodology + Data Policy published | Yes | Not started
7 | Static dashboard / company cards | Yes | Not started
8 | README demo asset (GIF/screens) | Yes | Not started
9 | Clean-machine install test | Yes | Not started
10 | MCP directory submissions prepared | Before campaign | Not started

## Cost Model
Zero-cost capacity model — does the free tier cover a daily 50-company refresh?
Input (blue = change me) | Value | Unit | Source / note
Companies tracked | 50 | count | PRD scope
Source items per company | 15 | items | news+podcast+edgar+web caps
Batch size (items per LLM call) | 15 | items | extract_claims_batch
Gemini 2.5-flash free requests/day | 20 | req/day | Observed live (quota error 2026-06-14)
Gemini 2.0-flash free requests/day | 200 | req/day | Est.; own daily quota
Gemini flash-lite free requests/day | 200 | req/day | Est.; own daily quota
Groq Whisper free requests/day | 2000 | req/day | Groq free tier (transcription)
Paid price per 1M input tokens (Flash) | 0.3 | USD | Est. if ever paid
Avg tokens per batch call | 6000 | tokens | ~15 items × ~400 tok
Calculations
Metric | Value | Unit | Note
LLM calls per company | 1 |  | batched
Total extraction calls/day (demand) | 50
Free capacity/day (3-model rotation) | 420 |  | each model has its own daily quota
Headroom (capacity − demand) | 370 |  | positive = fits in free tier
Fits in free tier? | YES — $0
Tokens/day used | 300000
Cost/day IF paid (not needed) | 0.09 |  | reference only
Cost/month IF paid (not needed) | 2.7 |  | reference only

## Risk Register
# | Risk | Likelihood (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status
1 | Data inaccuracy damages credibility | 3 | 5 | 15 | Provenance + confidence + ranges; never assert false precision; corrections |  | Open
2 | Audience ≠ pain (stars ≠ PMF) | 4 | 5 | 20 | Re-anchor ICP to AI-builder grounding; talk to first 50 users weekly |  | Open
3 | Free-tier LLM quota too low | 3 | 4 | 12 | Batching + multi-provider rotation; Cerebras for tokens |  | Open
4 | Legal/defamation on contradictions | 2 | 5 | 10 | Neutral 'public-source discrepancy' language; takedown policy |  | Open
5 | Source ToS / scraping blocks | 3 | 3 | 9 | Official APIs/RSS first; respect robots; conservative posture |  | Open
6 | Low launch adoption / HN flop | 3 | 4 | 12 | Portfolio of shots; contradiction hook; second-chance pool |  | Open
7 | Funded OSS rival pivots (e.g. OpenBB) | 2 | 4 | 8 | Speed + niche depth; interoperate, not only compete |  | Open
8 | Single-maintainer bandwidth | 4 | 3 | 12 | Keep scope narrow; community contributors; automation |  | Open

## Roadmap
Phase | Milestone | Status | Target | Notes
P0 Foundation | Specs + data model + reconciliation engine | Done |  | shipped
P1 Pipeline | Adapters + extraction + derivation + publish | Done |  | shipped
P1 Pipeline | Storage/IO + orchestration + dashboard + MCP | Done |  | shipped
P2 Data | Verified 10-company seed + contradictions | In progress |  | verify launch-grade
P2 Data | Whisper (Groq) live + EDGAR UA fix | In progress |  | podcast edge
P3 Launch prep | LICENSE + governance + issue templates | In progress |  | this batch
P3 Launch prep | Pitch deck + case study + demo GIF | Not started |  | showcase
P3 Publish | PyPI publish + set OPENPITCH_REMOTE | Not started |  | uvx install
P4 GTM | Run 30-day growth plan | Not started |  | after gates pass
P5 Scale | A2A agent · MENA adapters · rich sources | Not started |  | post-PMF